## Slide 1
Leading and lagging indicator to identify pattern
Monthly Review
Leading and Lagging Indicator
Implementation of near miss reporting program
Monthly Review
Near miss Reporting Program
Implementation of reward program on site.
Monthly Basis
Reward and Appreciation Program
External ISO 45001 Audit
Achieve 0 NC
ISO Certifications
Quarter 2
Implement Waste Management strategies
Monthly Waste Data Capture
Waste Management
Launch QHSE Survey for feedback
Annual Survey
QHSE Survey
Audit contractor on Quarterly basis
Quarterly contractors audit
Contractor Management
Appraise Program for QHSE team
Annual Review
Performance Appraisal
Quarter 4
Setup welfare program for each site
Quarterly welfare audit
Welfare Program
Inspection program for HIRA
Monthly inspections
Internal Inspection
Audit program to ensure compliance
Quarterly audit
Internal Audit
Training Program to ensure competency
Monthly training review meeting
Internal and External Training Program
Quarter 3
Setup QHSE Policies and ensure management commitment to implement policies
QHSE Policies
Setup and established SMART objectives for each site and department
QHSE Objectives
Quarterly visit
Safety Leadership Programme
Implement Hazard Identification and rectification program
Monthly Hazard review meeting
Hazard Identification Program
Quarter 1
QHSE Roadmap 2022