## Risk Settings
Risk Settings
| Severity Options |  |  | Likelihood Options
| Value | Severity |  | Value | Likelihood
| 1 | Insignificant |  | 1 | Rare
| 2 | Minor |  | 2 | Possible
| 3 | Moderate |  | 3 | Likely
| 4 | Major |  | 4 | Often
| 5 | Catastrophic |  | 5 | Frequent
| Responsible Person |  | Risk Type | Risk Impact Options |  | Risk Category
| Supervisor |  | Negative | Low |  | Health
| Manager |  | Opportunity | Moderate |  | Safety
| Staff |  |  | High |  | Environment
| Foreman |  |  |  |  | Quality
| Safety Team |  |  |  |  | Welfare
Legal
Risk Settings
Risk Identification
Risk Analysis
Risk & Opportunity Matrix
Dashboard
Risk Management Dashboard

## Risk Identification
Risk Identification
Sr.num | Risk Description | Risk Category
1 | Lack of Monitoring and Control | Safety
2 | Lack of Planning Sessions with the Team | Environment
3 | No Safety manager on Site | Safety
4 | Lack of General Support for Project Culture | Quality
5 | No Risk Management | Safety
6 | Unrealistic Estimates | Quality
7 | Little Top Management Support | Quality
8 | Bad Communication | Quality
9 | Workload of the People Involved | Welfare
10 | Deformation or Simply Lack of Scope | Quality
11 | Use a New Technology | Safety
12 | PPE Provision Issue | Safety
13 | New Opportunities | Safety
Risk Settings
Risk Identification
Risk Analysis
Risk & Opportunity Matrix
Dashboard
Risk Management Dashboard

## Risk Analysis
Risk Analysis
Sr.num | Risk Description | Risk Type | Likelihood | Cause of Risk | Consequence of Risk | Responsible Person | Severity | Impact on Cost | Impact on Time | Impact on Quality | Impact on Safety | Contingency Amount R | Overall Risk Exposure
1 | Lack of Monitoring and Control | Negative | Possible | Complete and Complex Schedules developed but not controlled | Lack of systematic follow-up | Staff | Minor | Moderate | Moderate | Moderate | Moderate | 12316 | Moderate
2 | Lack of Planning Sessions with the Team | Negative | Likely | Start the project without everyone involved understanding their role | The project will face numerous obstacles to its execution | Supervisor | Major | High | High | High | High | 13769 | High
3 | No Safety manager on Site | Negative | Often | Failure to hire a Safety Manager who is a leader and has knowledge | Lack of leadership and recognition by the parties involved | Staff | Moderate | High | High | High | High | 12411 | High
4 | Lack of General Support for Project Culture | Negative | Often | Lack of project management methodology | Weak control and management | Foreman | Major | Moderate | Moderate | Moderate | Moderate | 8828 | Moderate
5 | No Risk Management | Negative | Often | Lack of risk management | Project negatively impacted | Safety Team | Minor | Moderate | Moderate | Moderate | Moderate | 13806 | Moderate
6 | Unrealistic Estimates | Negative | Often | Wrong measurement of project costs | Incoherent Value Information | Staff | Catastrophic | High | High | High | High | 10169 | High
7 | Little Top Management Support | Negative | Often | Lack of follow-up by sponsors | Sponsors' lack of vision of the project's progress | Supervisor | Minor | Moderate | Moderate | Moderate | Moderate | 11937 | Moderate
8 | Bad Communication | Negative | Possible | Weak communication between involved parties | Wrong decisions made that can lead to negative impacts | Staff | Moderate | Moderate | Moderate | Moderate | Moderate | 2402 | Moderate
9 | Workload of the People Involved | Negative | Often | Failure to distribute tasks and responsibilities to involved parties | Exhausted and overworked professionals | Foreman | Major | High | High | High | High | 12937 | High
10 | Deformation or Simply Lack of Scope | Negative | Often | Lack of definition of project development guidelines | Control and monitoring of the project with failures | Safety Team | Major | High | Moderate | Moderate | High | 10255 | Moderate
11 | Use a New Technology | Negative | Possible | Identification of a more effective technology for project development | Productivity gain for the project | Manager | Insignificant | Moderate | Moderate | Moderate | Moderate | 2837 | Moderate
12 | PPE Provision Issue | Negative | Frequent | Lack of Safety Budget | Risk of injuries | Foreman | Moderate | High | High | High | High | 8951 | High
13 | New Opportunities | Opportunity | Likely | Discovery of new unidentified opportunities | Increased revenue gain | Manager | Major | Moderate | Moderate | Moderate | Moderate | 11052 | Moderate
Risk Settings
Risk Identification
Risk Analysis
Risk & Opportunity Matrix
Dashboard
Risk Management Dashboard

## Risk & Opportunity Matrix
Risk & Opportunity Matrix
Risk Matrix
|  | Frequent | [5 empty] | High
5
|  | Often | [5 empty] | 41.67%
| Likelihood | [6 empty] | Moderate
|  | Likely | [5 empty] | 7
58.33%
|  | Possible | [5 empty] | Low
0
|  | Rare | [5 empty] | 0%
|  |  | Insignificant | Minor | Moderate | Major | Catastrophic
Severity
Opportunities Matrix
|  | Frequent | [5 empty] | High
0
|  | Often | [5 empty] | 0%
| Likelihood | [6 empty] | Moderate
|  | Likely | [5 empty] | 1
100%
|  | Possible | [5 empty] | Low
0
|  | Rare | [5 empty] | 0%
|  |  | Insignificant | Minor | Moderate | Major | Catastrophic
Severity
Risk Settings
Risk Identification
Risk Analysis
Risk & Opportunity Matrix
Dashboard
Risk Management Dashboard

## Dashboard
Dashboard
| Total Qty | Risk |  | Opportunity |  | Contingency Value R
| 13 | 12 |  | 1 |  | 131670
|  |  | 120618 |  | 11052
Risk Settings
Risk Identification
Risk Analysis
Risk & Opportunity Matrix
Dashboard
Risk Management Dashboard

## Calculation (hidden)
Responsible Person
Supervisor | 2
Manager | 2
Staff | 4
Foreman | 3
Safety Team | 2
Risk Type
Negative | 12
Opportunity | 1
Contingency Value
Negative | 120618
Opportunity | 11052
Overall Risk Exposure
Low | 0
Moderate | 7
High | 5
Severity
Insignificant | 1
Minor | 3
Moderate | 3
Major | 5
Catastrophic | 1
Likelihood
Rare | 0
Possible | 3
Likely | 2
Often | 7
Frequent | 1